## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | Pass; RO; 10/5/21
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. |  | Pass; RO; 10/5/21
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | Pass; RO; 10/5/21
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. |  | Pass; RO; 10/5/21;
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. |  | Pass; RO;10/5/21;
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | Pass; RO;10/5/21
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | Pass; RO;10/5/21
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | Pass; RO;10/5/21; game can be started, but by typing valid name rather than selecting a button of some sort
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | Pass; RO;10/5/21
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | Pass;RO;10/6/21
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | Pass;RO;10/6/21
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | Pass; RO;10/5/21
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | Pass; RO;10/5/21
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | Pass; RO;10/5/21;can drop piece but causes error (future implementation)
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | Pass; RO;10/5/21
| Given I am a Player when I try to start a game with myself then the system should not allow me to start a game with myself. |  |  |  | Pass;RO;10/27/21
As a player I want each player to have twelve pieces with the same color so that I can identify which side I am on and know that no one has wrong pieces' setup | Given I am the host when I view the board then I should see twelve red checkers on the dark spaces closest to me. |  | Pass;RO;10/5/21
| Given I am not the host when I view the board then I should see twelve white pieces on the dark spaces closest to me. |  | Pass;RO;10/6/21
| Given I am the red player when I view the board then I should see the twelve white pieces on the dark spaces on the opposite side of the board. |  | Pass;RO;10/5/21
| Given I am the white player when I view the board then I should see the twelve red pieces on the dark spaces on the opposite side of the board. |  | Pass;10/5/21
As a player I want to play on an 8x8 grid pattern so that I know that I play on a Checker Game's board | Given a board when it is created then there should be 8 rows with 8 spaces per row. |  | Pass;RO;10/5/21
| Given a board when it is cread then there should be 32 white spaces and 32 dark spaces in an alternating pattern. |  | Pass;RO;10/5/21
As a player I want my piece to be round and red or white in color so that I know it is a checker | Given I am the host when I start a game with an opponent, then my color piece should be red. |  | Pass;RO;10/5/21
| Given I am a red player when I play the game then the red pieces should be closer to me |  | Pass;RO;10/5/21
| Given I am a white player when I play the game then the white pieces should be closer to me. |  | Pass;RO;10/6/21
| Given a colored piece is created when a piece is assigned a color then it should be places on a color square. |  | Pass;RO;10/6/21
As a player I want to let the red player move first so that a proper game of checkers is played and is following the American rules for checkers. | Given I am a Player when I make the first move then I should be able to move one of my pieces in a valid way. |  |  |  | Pass;RO;10/26/21;
| Given I am a white Player when the red Player makes the first move, then I can move. |  |  |  | Pass;RO;10/26/21;
| Given I am a red Player when the game starts then I can move any piece in the first row but no pieces in other rows. |  |  |  | Pass;RO;10/26/21;
As a player, I want to move my piece one square diagonally so that I can move my piece. | Given I am a Player when I try to move my piece diagonally to a new unoccupied space then I should be able to move the piece there. |  |  |  | Pass;RO;10/26/21;
| Given I am a Player when I try to move my piece diagonally to a new occupied space then I should not be able to move the piece there. |  |  |  | Pass;RO;10/26/21;
| Given I am a Player when I try to move vertically then I should not be able to move. |  |  |  | Pass;RO;10/26/21;
| Given I am a Player when I try to make a single move then the board of two players should be updated. |  |  |  | Pass;RO;10/26/21
As a player I want to know if a move can or cannot be done so that a winner and loser can be decided to end the game. | Given I am a Player when I attempt a valid move then I should be able to make that move. |  |  |  | Pass;RO;10/26/21;
| Given I am a Player when I attempt an invalid move then I should not be able to make that move. |  |  |  | Pass;RO;10/26/21;
| Given I am a Player when I attempt to move a piece more than one diagonal then I should not be able to make that move unless there is a possible jump move. |  |  |  | Pass;RO;10/26/21;
| Given I am a Player when I attempt to move a regular piece backwards then I should not be able to make that move. |  |  |  | Pass;RO;10/26/21;
As a player I want to be able to do a jump move if possible so that I can follow the American rules of checkers. | Given I am a Player when I can jump the other player's piece then I should have the ability to make that jump. |  |  |  | Pass;RO;10/26/21;
| Given I am a Player when I make a single jump move then I should have the ability to make another jump if possible. |  |  |  | Pass;RO;10/26/21
| Given I am a Player when there is a possible jump move then I should have to make that move. |  |  |  | Pass;RO;10/26/21
As a player I want to jump over an opponents piece diagonally so that I can capture an opponents piece and remove it from the board. | Given I am a Player when I can jump the other player's piece then I should have the ability to make that jump. |  |  |  | Pass;RO;10/26/21
| Given I am a Player when I can jump the other player's piece then I have to make that jump. |  |  |  | Pass;RO;10/26/21
| Given I am a Player when I jump the other player's piece then the piece that was jumped should be removed from the board. |  |  |  | Pass;RO;10/26/21
As a player I want to be able to jump multiple times diagonally in a move, captuing a piece with each jump so that I can capture multipe opponent pieces. | Given I am a Player when I have the opportunity to make multiple jumps then I should have the ability to take those jumps. |  |  |  | Pass;RO;10/26/21
As a player I want to sign-out so that I can stop playing games of checkers. | Given I am a signed in player when I click sign-out then I should be signed out and sent to the Home page |  | *do not test*
Given that I have not signed out when I see the Sign-in page then I must see a means to sign-out. (such as a link or button)
Given that I have not signed out when I click the sign out link then I must get a notification to confirm sign out action.
Given that I have not confirmed to sign out when I select yes in the notification bar then I must be able to sign out.
Given that I have not confirmed to sign out when I select no in the notification bar then I must be able to stay at the signed in page.
As a player, I want to be able to resign from the game at any time so that I can stop playing. | Given I am a Player when I join a game at the start and hit the resign button then I lose the game. | [5 empty] | Pass;RO;11/7/21
| Given I am a Player when I hit the resign button, in the middle of the game then I lose the game | [5 empty] | Pass;RO;11/7/21
| Given I am a Player when I hit the resign button, at the end of the game then I lose the game | [5 empty] | Pass;RO;11/7/21
As a player, I want to be able to leave the game and have it end once I leave so that I can stop playing. | Given I am a Player when I hit the resign button then the game will end. | [5 empty] | Pass;RO;11/7/21; after game is resigned and ended, new games can be started with the players involved in game but the game will not load for the opponent and trying to move a piece results in an error
| Given I am a Player when I hit the ressign button then I should be given an option to confirm using a confirmation bar. | [5 empty] | Pass;RO;11/7/21
| Given I am a Player when I confirm to resign then I lose the game. | [5 empty] | Pass;RO;11/7/21
| Given I am a Player when I don't confirm to resign then I keep playing the game. | [5 empty] | Pass;RO;11/7/21
As a player I want to watch others play a game so that I can learn how they play the game. | Given I am signed in when I select a game to watch then I should be able to watch it. |  | *do not test* |  |  |  | Pass;QT;11/14/21
| Given I am signed in when I want to watch a game then I should be able to see a list of current games being played. | [5 empty] | Pass;QT;11/14/21
| Given I watch a game when a player made a move then I expected to see an update on my spectating board | [5 empty] | Pass;QT;11/14/21
As a player I want to create an AI that follows the American Checker rule so that it won't follow other area rule. | Given we have an AI player when the AI plays checkers then the AI should play checkers by the American checker rules. |  | *do not test* |  |  |  | Pass;QT;11/14/21